Executive Summary: Course Demand and Revenue Forecasting

For government and public-sector education stakeholders

# Decision summary

EduPro’s historical data can support a transparent, monitored planning baseline for course demand and revenue. The dataset includes 10,000 transactions, 60 courses, 3,000 learners and 60 teachers. Recorded revenue is $911,323 over 2025-01-01 to 2025-12-30.

# What the initiative enables

- Evidence-based prioritization of course categories and course launches.

- Scenario planning for price, duration, level and rating attributes.

- Category-level comparisons for resource allocation and content-roadmap discussions.

- Transparent model monitoring using MAE, RMSE and R2 rather than opaque automated decisions.

# Safeguards for responsible use

- Keep forecasts advisory: do not use them as the sole basis for access, scholarship, educator or learner decisions.

- Protect learner privacy: the dashboard uses course-level aggregates and should not expose names, email addresses or individual transactions.

- Audit performance by course category, level and price band before relying on results for public funding or procurement decisions.

- Require human review for pricing and course-launch recommendations; test changes with small pilots before scaling.

# Recommended 90-day roadmap

| Period | Action | Outcome |
| --- | --- | --- |
| Days 1-30 | Confirm transaction/enrollment definitions; add course-teacher mapping and refund fields. | Trustworthy inputs |
| Days 31-60 | Run controlled price and launch experiments; capture impressions and conversions. | Causal evidence |
| Days 61-90 | Refresh time-based models, monitor error and publish an internal decision log. | Governed forecasting |

# Key limitation

This is an exploratory baseline based on only 60 courses. It is suited to prioritization and learning, not high-stakes automated decisions. Model performance must be re-evaluated as new courses and time periods are observed.